## Sheet1
Comprehensive Mitigation Action Items | Natural Hazards | [8 empty] | Category | Responsible Department | Schedule | Cost | Federal Funding Potential (NA, Unlikely, Possible, or Likely and Grant Program from Section XX | Weighted STAPLEE Criteria
| Flooding | High Wind and Tornado | Drough and Wildfire | Winter Sotrm | Earthquake | Hurricane | Sea Level Rise | Tsunami | Heat Wave |  |  | A. Daily |  |  | Costs (-1)/ Benefits (1)
[12 empty] | B. Monthly | Low = Minimal |  | Social | Technical (x2) | Administrative | Political | Legal | Economic (x2) | Environmental | STAPLEE Total
[10 empty] | 1. Physical Improvement |  | C. Annually | Intermediate = <$100,000
[10 empty] | 2. Program |  | D. 2013-2017 | High = >$100,000
[10 empty] | 3. Standard |  | E. 2018-2022
F. 2023 Onward
General Recommendations
1. NHMP Implementation, Maintenance and Review
Annual Review of Mitigation Efforts & Plan Implementation. The Planning Commission will monitor and evaluate progress in addressing action items in this Plan and include those accomplichments in its annual report to the Town. | X | X | X | X | X | X | X | X | X | 2 | CIP | C | Low = Minimal |  | 1 | 1 | -1 | 1 | 1 | 1 | 1 | 7
5-Year Review & Update of Natural Hazard Mitigation Plan. The Planning Commission will reconvene its mulit-agency Committee every 5 years to update the Plan. | X | X | X | X | X | X | X | X | X | 2 | CIP | D | Low = Minimal |  | 1 | 1 | -1 | 1 | 1 | 1 | 1 | 7
Capital Improvement Program. Use Capital Improvement Program (CIP) to set aside funds for infrastructure improvements to reduce loss of life and property during natural hazard (NH) events. | X | X | X | X | X | X | X | X | X | 2 | BOS / BOF, DPW, OEM, CREMPO, ETD | C | Intermediate = <$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 1 | 7
Benefit-Cost Analysis. Evaluate opportunities for public funding of mitigation projects on private property where public benefits exceed the cost for RL properties or for properties otherwise eligible for buy-out. | X | X | X | X | X | X | X | X | X | 2 | BOS / BOF, BO, TE, Assessor | C | Intermediate = <$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 1 | 7
Grants. Identify and apply for grants to fund infrastructure improvements and other mitigation tasks identified in this plan. | X | X | X | X | X | X | X | X | X | 2 | BOS / BOF, EDC, DPW, OEM | B | Low = Minimal |  | 1 | 1 | -1 | 1 | 1 | 1 | 1 | 7
0
2. Planning & Regulatory Standards | [21 empty] | 0
Land Use Regulation. Maintain, and strengthen as appropriate, subdivision and zoning regulations to make safer new roads and lots within flood zones. | X |  |  |  |  | X | X | X |  | 3 | BOS / BOF, ZC, PC, DPW, LUD, TE | C | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Flood Enforcement. Enforce through existing zoning, building and flood permitting processes, construction standards to minimize flood risks. | X |  |  |  |  | X |  | X |  | 3 | BOS / BOF, ZC, BO, TE | A | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Stormwater Management. Continue land use permitting that encourages storm water retention within new and redeveloping areas (rain gardens, curb less roads, etc.). | X |  |  |  |  | X | X | X |  | 3 | BOS / BOF, ZC, PC, IWWC, LUD, DPW, TE | B | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Public Transit Funding. Support regional transportation district (RTD) to facilitate movement of people without means of transportation prior to NH events. | X | X | X | X | X | X |  | X |  | 2 | BOS / BOF, DPW, OEM, CREMPO, ETD | C | Intermediate = <$100,000 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 8
FIRMs. Work with Federal Emergency Management Agency (FEMA) to incorporate updated Flood Insurance Rate Maps (FIRMs) into town’s planning, outreach and mitigation actions. | X | [6 empty] | X |  | 2 | BOS / BOF, all DEPTs | A | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Group Homes Permitting. Future permitting of these facilities shall include the requirement for the preparation of a disaster plan tailored to the needs of the specific clientele, or location of these facilities shall be discouraged in areas of known natural hazards. | X | X | X | X | X | X | X | X |  | 3 | ZC | D | Low = Minimal |  | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 7
Safer Location of Town Buildings. Future municipal structures should be located outside of known hazardous locations such as floodplains, to the extent possible. | X |  |  |  |  | X | X | X |  | 1 | BOS, BOF | D | Intermediate = <$100,000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 8
Local Sea Level Rise Study Committee. BOS should establish an ad-hoc committee to research medium and long-range impacts to coastal areas from SLR, to investigate possible mitigation actions and to assess legal, financial and policy implications. | X |  |  | X |  | X | X | X |  | 2 | BOS, BOF, PC, LUD, BO, TE | D | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Design Standards. Continue to implement State Building/Fire Code and local Flood Code for construction that minimizes loss of life and property damage due to NHs. Develop guidelines for HDC and ARB to retrofit existing structures in a manner that is respectful to significant or contributing structures and to overall neighborhood preservation. | X | X | X | X | X | X | X | X |  | 3 | BOS / BOF, ZC, BO, TE, ARB, HDC | A | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 8
Mandatory Wind Code Compliance. Ensure all building permit applicants construct their projects to meet 110 mile per hour wind load standard. |  | X |  | X |  | X |  |  |  | 3 | BOS, BO | A | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 8
3. Information Systems, Data Management & Analysis
GIS Database. Establish a comprehensive GIS database to better identify and assess areas, structures and populations potentially affected by natural disasters. These data will provide the town with information necessary to assess natural hazard risks and develop plans to mitigate risks to people and property. | X | X | X | X | X | X | X | X |  | 2 | PC |  | Low = Minimal |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 3
Oblique Imagery. Over the next five (5) years obtain oblique imagery in order to allow for assessment of such factors as extent of fire damage, compliance with building standards, identification of shoreline hardening and shoreline erosion and accretion. | X |  | X |  | X | X | X | X |  | 2 | BOS, BOF |  | Intermediate = <$100,000 |  | 1 | 0 | -1 | -1 | 0 | -1 | 0 | -3
Data for Plans. Use GIS database to develop better mitigation plans. | X | X | X | X | X | X | X | X |  | 2 | PC |  | Low = Minimal |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 5
Geographic Information System. Annually review and update as necessary existing town GIS data. | X | X | X | X | X | X | X | X |  | 2 | BOS / BOF, all DEPTs | C | Low = Minimal |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 5
Research Sea Level Rise Impacts. Seek grants funds to collaborate with an academic institution to research and study the social, economic, environmental and policy-related impacts from SLR. | X |  |  | X |  | X | X | X |  | 2 | BOS, BOF, PC | D | Low = Minimal | [8 empty] | 0
Dam Inventory. Update inventory of dams and assess downstream risks due to catastrophic failure. | X |  |  |  | X | X |  | X |  | 2 | BOS / BOF, DPW, DEEP | D | Intermediate = <$100,000 |  | 1 | 1 | -1 | -1 | -1 | -1 | 1 | -1
Risk Assessment. Use GIS to conduct NH risk assessments that identify potentially affected areas and depicts evacuation routes. | X | X | X | X | X | X | X | X |  | 2 | BOS / BOF, all DEPTs | C | Low = Minimal |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 6
Stormwater Infrastructure Inventory. Implement mapping and monitoring of catch basins, stormwater outfalls and related infrastructure. | X |  |  |  |  | X | X | X |  | 2 | BOS / BOF, DPW | C | Low = Minimal |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 6
Paper Records Preservation. Convert paper records maintained by the municipality to an electronic format, consistent with any State recommendations, to ensure their survival. Establish protocols for practices going-forward. | X | X | X | X | X | X |  | X |  | 2 | BOS / BOF, all DEPTs | D | Intermediate = <$100,000 |  | 1 | 1 | -1 | -1 | 0 | -1 | 0 | -1
Electronic Records Preservation. Design databases for records keeping. Create a back-up of existing electronic records, including geographic information system (GIS) data. | X |  | X | X | X | X |  | X |  | 2 | BOS / BOF, all DEPTs | D | Intermediate = <$100,000 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 5
Structural Reports. Continue to require structural engineering reports for expansion or alteration of buildings within the V zone. | X | [6 empty] | X |  | 3 | BOS / BOF, ZC, BO, TE | A | Low = Minimal |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 4
Firefighting Infrastructure Analysis. Evaluate existing firefighting infrastructure to identify needs for improvement to cover gaps in availability. | X | X | X | X | X | X | X | X |  | 2 | BOS / BOF, FD, FM | D | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 6
Zoning Map Audit. The Town should conduct a comprehensive audit of the zoning map to considering what changes might be advisable so that the free market investing is not misguided back towards areas that are at high risk from natural disasters. |  | X | X | [6 empty] | 3 | ZC | D | Low = Minimal |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 7
Open Space Criteria. Consider adding sea level rise to the Town’s considerations for preserving as open space those areas that flood waters will inundate. | X | [8 empty] | 2 | CC | D | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Amend Flood Ordinance. Consider adding a “freeboard” – an additional height above the flood level – to add a greater margin of safety. In the case of nonresidential structures, the insurance rates do not go down until a structure is flood proofed at least 0ne (1) foot above the BFE. | X |  |  | X |  | X | X | X |  | 2 | ZC | [10 empty] | 0
4. Physical and Infrastructure Improvements
Stormwater Infrastructure Maintenance. Provide for annual maintenance of stormwater infrastructure, including catch basins, detention basins and outfalls. | X |  |  |  |  | X | X | X |  | 2 | BOS / BOF, DPW | C | Intermediate = <$100,000 |  | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 6
Critical Facilities. Maintain and upgrade as necessary all facility mechanicals, such as generators, in municipal and other critical facilities. | X | X | X | X | X | X | X | X | X | 1 | BOS / BOF, all DEPTs | D | High = >$100,000 |  | 1 | 1 | 1 | 1 | 1 | -1 | 0 | 4
Telecommunication Tower Generators (Private). Evaluate whether generators are needed for back-up power at telecommunications facilities. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT |  |  |  | 1 | 1 | -1 | 0 | -1 | 0 | 0 | 1
Public Works Garage & Transfer Station Generator. Install a generator for back-up power. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT |  | High = >$100,000 |  | 1 | 1 | 1 | 1 | 1 | -1 | 0 | 4
Gas Station Generators. Encourage all privately-owned gas stations to install and maintain emergency back-up generators to insure availability of fuel during prolonged power outages. | X | X |  | X | X | X |  | X |  | 2 | BOS, OEM, PC | D | Intermediate = <$100,000 |  | 1 | 1 | 0 | 1 | -1 | 0 | 0 | 3
Road Evaluation. Evaluate roads to develop plans for improvement or elevation for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | C | Intermediate = <$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Elm Street Underpass. Resolve drainage/flooding problems to improve emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | High = >$100,000 |  | 1 | -1 | -1 | 1 | 1 | -1 | -1 | -3
College Street near North Cove Road. Evaluate to develop plans, and improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | Intermediate = <$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | -1 | 5
Banbury Crossing. Elevate to improve evacuation options, and explore options for secondary means of emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | Intermediate = <$100,000 |  | 1 | 1 | -1 | -1 | 0 | 1 | 0 | 3
South Cove Causeway. Evaluate to improve emergency access and evacuation and potential creation of a harbor of refuge. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | Intermediate = <$100,000 |  | 1 | -1 | -1 | 1 | 1 | -1 | -1 | -3
South Cove. Evaluate to develop plans, and improve for emergency access and evacuation potential dredging to improve flood stowage capacity and potential creation of a harbor of refuge. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, HMC, CREMPO, DOT | D | Intermediate = <$100,000 |  | 1 | -1 | -1 | 0 | 1 | -1 | -1 | -4
Plum Bank Road & Salt Meadow Road near Cornfield Park - Evaluate to develop plans, and improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | Intermediate = <$100,000 |  | 1 | 1 | -1 | -1 | 1 | -1 | 0 | 0
Sandy Point Road (Private). Evaluate to develop plans, and improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | Intermediate = <$100,000 |  | 1 | 1 | -1 | -1 | -1 | -1 | 0 | -2
Shetucket Trail. Review improvements and determine adequacy for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | Low = Minimal |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Fourth Avenue & Sunset Avenue. Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | 1 | -1 | -1 | 1 | -1 | 0 | 0
Old Post Road (Eastern End). Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | -1 | 5
Shetucket Trail-to-Bellaire Drive. Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Oweneco, Obed & Nehantic Trails. Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Mohican & Red Bird Trails. Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Maple Avenue. Develop plans to elevate approximately 1000' at northeast and near intersection with Main and College Streets; improve for emergency access and evacuation. | X | X | X | X |  | X | X | X |  | 1 | CIP,RTP, STIP | E | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Bokum-to-Barley Hill Road. Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | -1 | -1 | -1 | -1 | -1 | -1 | -7
Dwayne Road-to-Kitteridge Hill Road. Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | -1 | -1 | -1 | -1 | -1 | -1 | -7
Rock Ridge Drive-to-Dibble Road. Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | -1 | -1 | -1 | -1 | -1 | -1 | -7
Day Drive-to-Acorn Drive (Westbrook). Evaluate to develop plans; improve for emergency access and evacuation. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | -1 | -1 | -1 | -1 | -1 | -1 | -7
Off-street parking. Construct public parking lots to deter on-street parking that hinders emergency access and evacuation in high-density neighborhoods or high-intensity areas. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | E | High = >$100,000 |  | 1 | -1 | -1 | 1 | -1 | -1 | 0 | -4
North Main Street. Better organize on-street parking and partner with DOT/Amtrak to site a parking structure within walking distance of the train station. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT, AMTRAK | D | Low = Minimal |  | 1 | 1 | -1 | 1 | -1 | 1 | 0 | 4
Sheffield Street / Main Street. Better organize on-street parking and site a parking garage within walking distance of critical facilities, such as Town Hall, schools, Fire Department and Police Department. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, DPW, OEM, CREMPO, DOT | D | Low = Minimal |  | 1 | 1 | -1 | 0 | 1 | 1 | 0 | 5
Pool. Construct a public pool to enhance ability to swim of both emergency responders and residents. | X |  |  |  |  | X |  | X |  | 1 | BOS / BOF, DPW, OEM, DEEP | D | High = >$100,000 |  | 1 | 1 | -1 | 0 | 1 | -1 | 0 | 1
Obed Heights Dam. Evaluate Obed Heights Reservoir dam; work with property owners and State DEEP for repairs as needed. | X |  |  |  | X | X |  | X |  | 2 | BOS / BOF, DPW, DEEP | E |  |  | 1 | 0 | 0 | 0 | -1 | 0 | 0 | 0
Private Dam Evaluation. Evaluate remaining privately-owned dams; work with property owners and State DEEP for repairs as needed. | X |  |  |  | X | X |  | X |  | 1 | BOS / BOF, DPW, DEEP | C |  |  | 1 | -1 | 0 | 0 | -1 | 0 | 0 | -2
Town Dam Evaluation. Evaluate remaining Town-owned dams; work with DPW and State DEEP for repairs as needed. | X | X | X | X |  | X | X | X |  | 1 | BOS / BOF, DPW, DEEP | D |  |  | 1 | -1 | -1 | 0 | 1 | 1 | 0 | 1
Stormwater Management. Continue to use best management practices (BMPs) as described in the Connecticut DEEP Stormwater Management Guidelines on a site-by-site basis as advised by a professional engineer. | X |  |  |  |  | X | X | X |  | 2 | BOS / BOF, ZC, PC, IWWC, LUD, DPW, TE | B | Low = Minimal |  | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 6
Nibang Ave. End near Route 154 is under water after most big rains and storms and is lower than the land surrounding it. Raise and rebuild. | X |  |  |  |  | X | X | X |  | 1 | BOS/BOF/DPW/BW | D | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Sequassen Ave. Raise and rebuild to address flooding issues. | X |  |  |  |  | X | X | X |  | 1 |  | D | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
Borough property north of seawall near Pattaquesett Ave. Severely scoured in the last 2 major storms. A permanent fix has been recommended by FEMA. Repaid based on FEMA recommendations is needed. | X |  |  |  |  | X | X | X |  | 1 |  | D | High = >$100,000 |  | 1 | 1 | -1 | 1 | 1 | 1 | 0 | 6
5. Public Information and Outreach
Preparedness Webpage. Keep Town website updated with NH preparedness information, including hazard areas, evacuation routes deemed appropriate per NH event and locations of shelters. | X | X | X | X | X | X |  | X | X | 2 | BOS / BOF, all DEPTs | B | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 8
Recovery Webpage. Post on Town website information about recovery assistance following NH events. | X | X | X | X | X | X |  | X |  | 2 |  | B | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 8
Wildfire Education. Educate the public about potential hazard of wildfire caused by campfires or open burning. |  |  | X |  | X |  |  |  |  | 2 | BOS / BOF, FD, FM | C | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Hotline. Publicize emergency "hotline" phone number or website for public information and volunteer support. | X | X | X | X | X | X |  | X | X | 2 | BOS / BOF, OEM | A | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 8
Drought Education. Coordinate with CWC on public education and public serve announcements during droughts. |  |  | X | [6 empty] | 2 | BOS / BOF, OEM, CWC | C | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 7
Educate About Risk Based on Where People Live. Educate residents at high risk due to demographic or social attributes about the risk(s) relative to the areas that they populate. | X | X | X | X | X | X | X | X | X | 2 | PC, ZC, Social Services |  | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 6
Outreach. Promote owner participation in mitigation efforts to protect their property. | X | X | X | X | X | X | X | X |  | 2 | BOS / BOF, LUD, BO, EDC | A | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 6
Repetitive Loss Elevation Funding. Encourage RL property owners to obtain assistance from DEEP and FEMA to acquire hazard mitigation funds to elevate structures where appropriate. | X |  |  |  |  | X |  | X |  | 2 | BOS / BOF, ZC, BO, TE | A | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 6
Conservation Planning. Educate the public about how the Town uses planning, regulation, and ordinances to mitigate NHs via LID, aquifer recharge, riparian buffer, rain gardens, open burning ordinances, house numbering, etc. | X | X | X | X |  |  | X | X |  | 2 | BOS / BOF, CC, IWWC | B | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 7
Neighborhood Mitigation. Engage neighborhood associations annually to participate in implementing the NH Mitigation Plan. | X | X | X | X | X | X | X | X |  | 2 | BOS / BOF, all DEPTs, RiverCOG | C | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 6
Incident Notification System. Enlist public participation through public workshops to develop methods for notification of hazard events and emergencies. | X | X | X | X | X | X | X | X | X | 1 | BOS/BOF OEM | D | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 6
6. Actions to Reduce Risk and Minimize Impacts During NH Events
Refuges of Last Resort. Identify refuges of last resort for those unable to reach designated shelter. | X | X | X | X | X | X |  | X |  | 2 | BOS / BOF, OEM | D | Low = Minimal |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2
Immobile Evacuees. Review annually the program to evacuate persons without means of transport, including registration and house numbering. | X | X | X | X | X | X |  | X | X | 2 | BOS / BOF, OEM | C | Low = Minimal |  | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 5
Animal Shelter. Expand dog pound to shelter more animals/pets and participate in regional pet sheltering center. | X | X | X | X | X | X |  | X |  | 1 | BOS / BOF, OEM | D | Intermediate = <$100,000 |  | 1 | -1 | 0 | 0 | 1 | -1 | 0 | -2
Natural Hazard Training. Continue to train and educate emergency responders about mitigating NHs. | X | X | X | X | X | X | X | X |  | 2 | BOS / BOF, OEM | C | Low = Minimal |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3 | Are we doing this?
Land Acquisition. Advance an assertive land acquisition plan to reserve vacant land subject to NHs. | X | X | X | X | X | X | X | X |  | 1 | BOS / BOF, LAC | C | High = >$100,000 |  | 1 | 1 | 0 | 0 | 1 | -1 | 1 | 3
Street Tree Program. Implement a tree hazard management program to encourage appropriate planting and maintenance practices to minimize future storm damage to buildings, utilities and streets. | X | X | X | X |  | X |  | X |  | 2 | BOS / BOF, DPW, TW | C | Low = Minimal |  | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 5
Dune Restoration. Implement dune restoration and marshland protection techniques for flood storage and surge protection. | X |  |  |  |  | X | X | X |  | 1 | BOS / BOF, LAC, CC, DPW, DEEP | D | Intermediate = <$100,000 |  | 1 | 0 | 0 | 0 | 1 | -1 | 1 | 1
Drought Study. Conduct town-wide study of ground- and surface water capacity as it relates to planning for droughts. |  | X | [7 empty] | 2 | BOS / BOF, FD, FM, CWC | E | Intermediate = <$100,000 |  | 1 | 0 | 0 | 0 | 1 | -1 | 1 | 1
Underground Utilities. Require underground utilities for new development; require retrofitting during redevelopment of existing sites to bury utilities where appropriate to mitigate NHs. | X | X | X | X | X | X | X | X |  | 3 | BOS / BOF, ZC, PC, IWWC, LUD, DPW, TE | E | Low = Minimal |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 3
Recovery & Reconstruction Plan. Develop a post-disaster recovery and reconstruction plan to re-establish infrastructure and public services, etc. damaged or destroyed by any NH event, including establishment of a "rainy day" fund in case Federal assistance is insufficient or delayed. | X | X | X | X | X | X | X | X |  | 2 | BOS / BOF | D | Intermediate = <$100,000 |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Risk Reduction. Develop a strategy and funding program to elevate or relocate structures of flood-prone properties or acquire RL properties that request a "buy-out". | X |  |  |  | X | X | X | X |  | 1 | BOS / BOF, LUD | D | High = >$100,000 |  | 1 | 0 | 0 | 0 | 1 | -1 | 0 | 0
Group Homes Disaster Plans. The Town should offer to work with each of the existing facilities to prepare a disaster plan, if they do not already have one. | X | X | X | X | X | X | X | X | X | 2 | ZC | D | Low = Minimal |  | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 4
Tenant Notification. Develop a mechanism for tenants to register for disaster notification. | X | X | X | X | X | X |  | X | X | 2 | BOS, ZC | D | Low = Minimal |  | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 4 | Reverse 911, CT Emergency Notification System
Landlord Incentives. Research what kind of incentives would motivate land owners to make the additional investment that would reduce potential damages to their properties and loss of life of their tenants. | X | X |  |  | X | X |  |  | X | 3 | BOS, ZC, BO | D | Low = Minimal |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2
Municipal Buildings Capable of being Shelters. Future investment in municipal structures should include funding for new construction or renovation that will assure the structure is compliant with the standards for use as a shelter, to the extent possible. | X | X | X |  | X | X | X |  | X | 1 | BOS, BOF | D | High = >$100,000 |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Caches. Consider creating stores of emergency supplies in areas of town that will be cut off during major flooding events. | X | X | X | X | X | X | X | X |  | 1 | BOS, BOF | E | Intermediate = <$100,000 |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Drinking Water Cache. Install drinking water tanks with a supply of bleach for private well water purification. | X |  | X |  |  | X |  |  |  | 3 | PC, ZC | E | Intermediate = <$100,000 |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Boats. Identify places where people could store their boats during flooding and hurricane events that would reduce the damage to them and that they cause to the waterfront infrastructure when they break from moorings. | X | X | X |  |  | X |  |  |  | 2 | PC, ZC, HC | E | Low = Minimal |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Cooperative Agreements for Shelters. Develop supporting documentation and encourage the Board of Selectmen to establish agreements for shelters that can provide specialized services, throughout the region. Shelters with the capacity to provide for companion pets and medical equipment needs for individuals with disabilities are two examples of such specializations. Support changes in the laws that require every town to provide facilities capable of serving the most severe of handicapped individuals such that towns could pool their resources to better serve these individuals and their families by giving them the option to go to a regional shelter better equipped to handle theirs, and their family’s, needs. | X | X | X | X | X | X | X | X |  | 2 | BOS, BOF | E | Low = Minimal |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Interpretation in Shelters. Request information regarding the need for providing non-English language speakers during natural disasters from the Old Saybrook School administration; and coordinate a shared service for non-emergency and emergency operations. | X | X | X | X | X | X |  | X |  | 2 | BOS, BOF | D | Low = Minimal |  | 1 | 0 | 0 | 0 | 1 | -1 | 0 | 0
Local Social Resources. Identify local resources to assist with those populations (i.e. elderly, disabled, non-English speakers, who may frequent, reside, or work) in Old Saybrook. Seek grants to provide funding for developing more detailed data to assist in the social – demographic analysis of how Chester will be affected by natural hazards. | X |  | X | X | X | X |  | X |  | 2 | BOS, BOF | D | Low = Minimal |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Social –Demographic Impacts. Seek grants to provide funding for developing more detailed data to assist in the social – demographic analysis of how Old Saybrook will be affected by natural hazards. | X | X | X | X | X | X |  | X | X | 2 | BOS, BOF | E | Low = Minimal |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Temporary Housing. Evaluate the need for post disaster housing for residents displayed by flood or another natural disaster. | X | X | X |  | X | X |  | X |  | 2 |  | D | Low = Minimal |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Identify Purchase Zones. Evaluate the benefit of purchasing destroyed properties as open space as an alternative to reuilding. Identify specific areas where such a program could benefit residents and mitigate loss. | X | X | X |  | X | X | X | X |  | 2 |  | E | Low = Minimal |  | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 3
Evaluate Benefits of Engineered Town Beach. Investigate benefit cost of engineered designs for Town beaches so they could be eligible for recovery funding. | X |  |  | X |  | X | X | X |  | 1 |  | D | Low = Minimal |  | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 5
7. Miscellaneous
Post Disaster School Arrangements. Establish reciprocal arrangements with other school districts for getting students back into classes during extended recovery periods. | X | X | X | X | X | X |  | X |  | 2 | BOS, BOE | E | Low = Minimal |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Potential Financial Impact of Recent Storms. Provide a reference point; ask the Tax Assessor if he can provide a figure for the lost property value resulting from Tropical Storm Irene and Storm Sandy and the potential lost tax revenue if the structures are not restored before the next taxing period. |  |  |  | X |  | X |  |  |  | 2 | BOS, BOF | D | Low = Minimal |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 6
Potential Financial Impact of Probable Events. Estimate the municipal tax revenue that could potentially be lost in various events to provide the Board of Selectmen and Board of Finance with an idea of how large a “rainy day” fund might be necessary to cover that post disaster period when there would be “minimal income and maximum output” [to paraphrase former First Selectman, Michael Pace] of public funds at all levels of government. | X | X | X | X | X | X | X | X |  | 2 | BOS, BOF | D | High = >$100,000 |  | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Forest Management Plan. Hire a consulting forester to establish a forest management plan to enable ability of firefighters to access forest fires during periods of drought. |  |  | X | [6 empty] | 2 | BOS / BOF, PRC, FD, FM | E | Intermediate = <$100,000 |  | 1 | 1 | 0 | 0 | 1 | -1 | 1 | 3
Park Maintainer. Fund a dedicated Park Maintainer to act as steward of public open spaces, including parks, forests, drainage basins, conservation easements, coastal access points, and forests, and to mitigate NHs at Town-owned properties. | X |  | X | X |  |  |  | X |  | 2 | BOS / BOF, PRC, CC | D | Intermediate = <$100,000 |  | 1 | 1 | 0 | 0 | 1 | -1 | 1 | 3
Note on S3: Sandy Prisloe:b perhaps CN should run each action item by CF to see if BOS supports or not